## Project Plan
ID | Segment | End Date | Who | Description | Dependencies | Completed H | Completed A | Completed D | Completed S
1 | 1 | 2023-05-18 | David | Create github repo |  |  |  | X
2 | 1 | 2023-05-18 | All | Explore data
3 | 1 | 2023-05-18 |  | Define the question
4 | 1 | 2023-05-18 |  | Mock up of database
5 | 1 | 2023-05-18 |  | ERD of database and description
6 | 1 | 2023-05-18 |  | Mock up machine learning model
7 | 1 | 2023-05-18 | Heather | A detailed README.md file (20 points)
8 | 1 | 2023-05-18 |  | At least four commits per team member (20 points)
9 | 1 | 2023-05-18 |  | A database that stores at least two tables (or collections) for the project (20 points)
10 | 2 | 2023-05-25 |  | Updated README.md file
11 | 2 | 2023-05-25 |  | At least eight total commits per team member (20 points)
12 | 2 | 2023-05-25 |  | Updated database that stores at least two tables (or collections) for the project (20 points)
13 | 2 | 2023-05-25 |  | A machine learning model, including a confusion matrix and an accuracy score.
14 | 2 | 2023-05-25 |  | Presentation Slide deck
15 | 2 | 2023-05-25 | All | Mock Presentation
16 | 2 | 2023-05-25 |  | Testing the model
17 | 3 | 2023-06-01 |  | A dashboard that has at least one interactive element
18 | 3 | 2023-06-01 |  | Finalize README.md file
19 | 3 | 2023-06-01 |  | Quality Checks
20 | 3 | 2023-06-01 |  | Prep for Presentation (update slide deck)
21 | 3 | 2023-06-01 | All | Mock Presentation
22 | 3 | 2023-06-01 | All | Presentation
23 | Post Project | 2023-06-01 | All | Written Assessment - Self-Assessment
24 | Post Project | 2023-06-01 | All | Written Assessment - Project and Team Summary

## Upcoming Absence
Heather | Tuesday May 23